## Description
CS312-- Software Engineering
Assignment: | 1
Due date: | 2022-02-21 | 12:00 Noon
Name of this file: | 1.xls
Objective: | To gain experience using a rudimentary process model
Assignment: | Write a program to input* a set of n numbers and
1) calculate and print the average of the set
2) calculate and print the standard deviation** of the set
3) calculate and print the median*** of the set
* Input = read from either file or keyboard, your choice
** The median for an even number of items is the average of the two midpoint values when the items are arranged in sorted order; the median for an odd number of items is the middle value when the items are arranged in sorted order.
Notes on Requirements: | - Your program shall be capable of processing up to (and including) 100 entries.
- Your program shall print either valid numbers or meaningful error messages, where appropriate.
- Use the following data to test your program:
|  | Test Set 1 | Test Set 2 | Test Set 3
|  | 160 | 415 | 129.8198
|  | 135 | 804 | 361.5276
|  | 179 | 1031 | 177.911
|  | 177 | 597 | 71.3865
|  | 225 | 330 | 3.7914
|  | 99 | -74 | 262.72
|  | 151 | -31 | 46.2323
|  | 166 | 80
|  | 101 | 279
|  | 156 | -27
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- In following the script for PSP, you need not use a pure waterfall lifecycle; you are welcome to use any development lifecycle as long as you document in chronological order on your time recording log the phase activities you enacted (together with the duration of each activity) to accomplish the homework. If you use a waterfall approach, your time recording log would show plan-design-code-compile-test-postmortem activities. If you use a design-a-little/code-a-little/test-a-little approach, your time recording log might show plan-design-code-compile-test-code-compile-test-etc.
- Be honest in your data. Your grade depends on how you follow the process, not on the speed of your work or the number of defects found.
Deliverables: | - Complete all cells highlighted in yellow. When submitting your assignment, please upload the entire spreadsheet to your homework submission area on OneDrive.
- Paste your source code and test results in the appropriately marked areas herein.
- When complete, upload the spreadsheet to OneDrive
- log on to WebCT
- select the icon titled "Homework Turn-in"
- click on the table entry that says "[Edit]". This is your private submission area; everyone has a different area.
- Click on the button titled "upload", then the button titled "Browse". A dialog box will pop up showing the structure of the files on your client computer. Select the Excel file you want to upload. (Please retain the original filename.) Note that WebCT shows files with an HTML extension by default; you'll need to change the file chooser to *.* to see all the files in your directories. Click the "OK" button and follow the directions. WebCT will indicate when your fill has been successfully uploaded. Please do not create a separate subdirectory for your homework.
- I will download your file, grade it, and return it to your assignment download area.

## Process
Process Script
Entry |  | - Problem description
- Defect standard type
|  |  | Type: | Defects resulting from problems with:
|  |  | Documentation | comments, message
|  |  | Syntax | spelling, punctuation, typos, improper programming language grammar
|  |  | Build, package | change management, library, version control
|  |  | Assignment | declaration, duplicate names, scope, limits
|  |  | Interface | module calls and references, user formats
|  |  | Checking | error messages, inadequate bound/type/format checking
|  |  | Data | structure, content
|  |  | Function | logic, pointers, loops, recursion, computation, functional defects
|  |  | System | configuration, timing, memory
|  |  | Environment | programming tools
Tasks | 1. Planning | - Determine initial expected results
- Estimate and record "planned" statistics
n. Record time spent planning
| 2. Development | - Design; log time spent
- Code; fix and log all defects found; log time spent
- Compile; fix and log all defects found; log time spent
- Test; update expected results as necessary; fix and log all defects found; log time spent
n. Record actual results; attach source code
| 3. Post Mortem | - Calculate and record "actual" process statistics
Exit |  | - tested program
- completed worksheet
Quality checks
General
Are all regions highlighted in yellow complete?
Does the worksheet reflect a faithful record of information?
Has this assignment been uploaded to OneDrive as a single file with the appropriate file name?
Project Plan Summary
Was the planned time and size determined before development and not altered after development?
Were initial "expected results" calculated before coding began?
Is the actual size calculated according to your counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the following process phases:plan, code, compile, test, post mortem? (All other phases are optional.)
Is post mortem the final phase?
Does the time recording log reflect the actual lifecycle used?
Defect Log
Is each defect accompanied by a description in the "comment" field?
Are defects recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count?
Are the dates and times in the defect log consistent with the dates and times in the time recording log?
Test Report
Are actual results included in a readable format?
Do actual results support expected results?
Source Code
Is source code attached?
Does the code reflect your coding standard?
Will the code compile without change when copied from the spreadsheet?
Does the code take into consideration error conditions?
Does the code fulfill the assignment requirements?

## Assignment
Name: |  | Shagufta Anjum
Roll No: |  | 19XJ1A0568
Language |  | C++
Changes have been made to 1.xls since the last homework submission:
Assignment: |  | 1
Due Date: |  | 2022-02-21
Name of file: |  | 1.xls
Table of Contents
go to | Instructor Assessment:
go to | Project Plan Summary
go to | Time Log
go to | Defect Log
go to | Size Estimation
go to | Task Plan
go to | Schedule
go to | Operational Scenario
go to | Functional Specification
go to | Test Report
go to | Lessons Learned
go to | LOC Counting Std
go to | LOC Coding Std
go to | Size Estimation
go to | Conceptual Design
go to | Review Checklists
go to | Task Plan
go to | Schedule
go to | Operational Spec
go to | Functional Spec
go to | Logic Spec
go to | State spec
go to | Source Code
Instructor Assessment
Aspect | Criteria | Possible Score | Score | Comment
Process
| Project Plan | 2
| Time Log | 2
| Defect Log | 2
| Test Report | 2
| Source | 2
| Schedule | 0
| Design | 0
Product | Coding Standards | 3
| Rqmts met | 2
| Total | 15 | 0
Standards
Start date: | 2010-01-01
End date: | 2030-01-01
Phases: | Planning
Design
Code
Compile
Test
Postmortem
Design Review
Code Review
Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Setup
Text
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Project Plan Summary
|  | Plan | Actual
Summary
Loc/hour |  | #REF! | 0
Duration (min) |  | 180 | 240
Actual Duration
Cost-Performance Index |  | 1 | 0.75
% Reused
Test Defects/KLOC
Total Defects/KLOC
Appraisal COQ
Failure COQ
A/F COQ Ratio
|  | Plan | Actual | To Date
Program Size (LOC)
Base (B) |  | 0
Deleted (D) |  | 0
Modified (M) |  | 0
Added (A) |  | 0 | 73
Reused (R) |  | 0 |  | #REF!
Total New&Changed (N)
Total LOC(T) |  | 60 | 73 | 73
Total New Reused |  | 0 |  | #REF!
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Planning |  |  | 44 | 44 | 18.33%
Design |  |  | 14 | 14 | 5.833%
Design Review |  |  | 21 | 21 | 8.75%
Code |  |  | 87 | 87 | 36.25%
Code Review |  |  | 21 | 21 | 8.75%
Compile |  |  | 9 | 9 | 3.75%
Test |  |  | 25 | 25 | 10.42%
Postmortem |  |  | 19 | 19 | 7.917%
TOTAL |  | 180 | 240 | 240 | 100%
Defects Injected
Planning |  |  | 0 | 0
Design |  |  | 0 | 0
Design Review |  |  | 0 | 0
Code |  |  | 7 | 7
Code Review |  |  | 1 | 1
Compile |  |  | 0 | 0
Test |  |  | 0 | 0
Postmortem |  |  | 0 | 0
TOTAL DEVELOPMENT |  |  | 8 | 8
Defects Removed
Planning |  |  | 0 | 0
Design |  |  | 0 | 0
Design Review |  |  | 0 | 0
Code |  |  | 4 | 4
Code Review |  |  | 0 | 0
Compile |  |  | 0 | 0
Test |  |  | 4 | 4
Postmortem |  |  | 0 | 0
TOTAL DEVELOPMENT |  |  | 8 | 8
AFTER DEVELOPMENT
go to Table of Contents
Time Recording Log
Date | Start | Stop | Interrupt | Delta | Phase | Comments
2022-02-17 | 20:30 | 21:05 | 10 | 25 | Planning | Determined the expected results
2022-02-18 | 7:45 | 8:10 | 6 | 19 | Planning | Decided on the environment and algorithms to use
2022-02-18 | 8:14 | 8:20 |  | 6 | Design | Designed the functions to be used
2022-02-19 | 10:18 | 10:26 |  | 8 | Design | Design of I/O method
2022-02-19 | 10:50 | 11:17 |  | 27 | Code | Coding I/O process
2022-02-19 | 11:18 | 11:20 |  | 2 | Compile
2022-02-19 | 11:20 | 11:30 |  | 10 | Code | Coding the mean and median functions
2022-02-19 | 11:32 | 11:34 |  | 2 | Compile
2022-02-19 | 11:36 | 11:53 |  | 17 | Code | Debugging errors
2022-02-19 | 11:54 | 11:55 |  | 1 | Compile
2022-02-20 | 8:11 | 8:14 |  | 3 | Code | Debugging errors
2022-02-20 | 8:15 | 8:16 |  | 1 | Compile
2022-02-20 | 8:16 | 8:20 |  | 4 | Test | Testing mean and median functions
2022-02-20 | 8:20 | 8:24 |  | 4 | Code | Coding Std dev function
2022-02-20 | 8:25 | 8:26 |  | 1 | Compile
2022-02-20 | 8:27 | 8:30 |  | 3 | Test | Testing Std dev function
2022-02-20 | 10:20 | 10:32 |  | 12 | Code | Fixing logic errors
2022-02-20 | 10:32 | 10:33 |  | 1 | Compile
2022-02-20 | 10:33 | 10:45 |  | 12 | Test | Testing I/O and all functions
2022-02-21 | 9:00 | 9:22 | 5 | 17 | Code Review
2022-02-21 | 9:23 | 9:37 |  | 14 | Code | Added error messages
2022-02-21 | 9:38 | 9:39 |  | 1 | Compile
2022-02-21 | 9:39 | 9:45 |  | 6 | Test | Recorded final results
2022-02-21 | 9:45 | 9:49 |  | 4 | Code Review
2022-02-21 | 9:49 | 10:25 | 15 | 21 | Design Review
2022-02-21 | 10:26 | 10:50 | 5 | 19 | Postmortem | Recorded actual statistics
go to Table of Contents
Defect Log
Date | Number | Type | Inject | Remove | Fix Time | Fix Defect | Description
2022-02-19 | 1 | Syntax | Code | Test | 5 | 1 | Converting string to float
2022-02-19 | 2 | Function | Code | Code | 8 | 2 | Error in returning pointer from array
2022-02-19 | 3 | Function | Code | Test | 2 | 3 | Error in loop statement
2022-02-20 | 4 | Syntax | Code | Test | 3 | 4 | Opening file
2022-02-20 | 5 | Function | Code | Code | 10 | 5 | Error in formula of standard deviation
2022-02-20 | 6 | Checking | Code | Test | 2 | 6 | Input array type
2022-02-21 | 7 | Checking | Code Review | Code | 8 | 7 | Input type and file format checking
2022-02-21 | 8 | Function | Code | Code | 3 | 8 | Assignment of pointer to float
go to Table of Contents
Size Estimate
Base Program |  |  |  |  | LOC
Base Size (B)
LOC Deleted (D)
LOC Modified (M)
Projected LOC
| Base Addition | Type | Methods | Rel Size | LOC
0
0
0
0
0
0
0
0
0
0
0
0
| Total Base Additions (BA) |  |  |  | 0
| New Objects | Type | Methods | Rel Size | LOC | New Reuse?
0
0
0
0
0
0
0
0
0
0
0
| Total New Objects (NO) |  |  |  | 0
| Reused Programs |  |  |  | LOC
| Reused Total (R) |  |  |  | 0
Calculations
| Projected LOC |  |  |  | 0
| Regression Parm (B0) |  |  |  | 0
| Regression Parm (B1) |  |  |  | 1
| Estimated New and Changed LOC (N) |  |  |  | 0
| Estimated Total LOC (T) |  |  |  | 0
| Estimated Total New Reused |  |  |  | 0
Prediction Range
Upper Prediction Interval
Lower Prediction Interval
Prediction Interval Percent
go to Table of Contents
Historical Size Data
Size Matrix (LOC/Method)
| VS | S | M | L | VL
Calculation | 0 | 0 | 0 | 0 | 0
Data | 0 | 0 | 0 | 0 | 0
I/O | 0 | 0 | 0 | 0 | 0
Logic | 0 | 0 | 0 | 0 | 0
Setup | 0 | 0 | 0 | 0 | 0
Project History
Project Name | LOCE | LOCA | T
2A
3A
4A
5A
LOCE x LOC A |  | B0= | 0 |  | bad data -- value of 0 assumed
|  | B1= | 1 |  | bad data -- value of 1 assumed
LOCE x T |  | B0= | 0 |  | bad data -- value of 0 assumed
|  | B1= | 1 |  | bad data -- value of 1 assumed
LOCA x T |  | B0= | 0 |  | bad data -- value of 0 assumed
|  | B1= | 1 |  | bad data -- value of 1 assumed
Duration Calculation Method:
go to Table of Contents
Task Plan
Task |  | Plan |  |  |  |  | Actual
# | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Minutes | Date | Date | Earned Value | Cum. Earned Value
go to Table of Contents
Schedule
|  | Plan |  |  | Actual
Day # | Date | Direct Minutes | Cumulative Minutes | Cumulative Planned Value | Direct Hours | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
go to Table of Contents
Operational Specification
Source | Step | Action |  |  |  | Comments
go to Table of Contents
Functional Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
Proxie Name: |  | Parent: |  | Attributes:
Method Declaration: |  | Method External Specification
go to Table of Contents
Logic Specification
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
Module Name:
Includes:
Declarations:
# | Pseudocode
go to Table of Contents
Test Report
Expected Results:
|  |  | Test Set 1 | Test Set 2 | Test Set 3
|  |  | 160 | 415 | 129.8198
|  |  | 135 | 804 | 361.5276
|  |  | 179 | 1031 | 177.911
|  |  | 177 | 597 | 71.3865
|  |  | 225 | 330 | 3.7914
|  |  | 99 | -74 | 262.72
|  |  | 151 | -31 | 46.2323
|  |  | 166 | 80
|  |  | 101 | 279
|  |  | 156 | -27
|  | average = | 154.9 | 340.4 | 150.484
|  | std = | 37.379 | 377.064 | 127.122
|  | median = | 158 | 304.5 | 129.82
Actual results: |  | Test Set 1: | Average = | 154.9
|  |  | Median = | 158
|  |  | Standard Deviation = | 37.379
|  | Test Set 2: | Average = | 340.4
|  |  | Median = | 304.5
|  |  | Standard Deviation = | 377.064
|  | Test Set 2: | Average = | 150.484
|  |  | Median = | 129.82
|  |  | standard Deviation = | 127.122
End Test Report
go to Table of Contents
Lessons Learned
Problems of Importance
1 | Checking for appropriate input
2 | Planning each function required and utility code in the planning phase
3 | Using correct data structures and variable datatypes
4
5
Proposal for Improvements
1 | Plan for smaller errors in advance - for example, errors in type conversion, loops, etc.
2 | Be familiar with syntax in advance
3
4
5
Notes and Comments
1
2
3
4
5
go to Table of Contents
Source Code
Paste source code here. (1) copy your code to the clipboard, 2) click on the "PASTE ME" cell, 3) paste.)
#include <iostream>
#include <fstream>
#include <cmath>
#include <algorithm>
using namespace std;
// To diaply an array of numbers
void show(float* nums, int count){
for (int i=0; i<count; i++){
cout << nums[i] << " ";
}
cout << endl;
}
// To calculate mean
float mean(float* nums, int count){
float sum=0;
for(int i=0; i<count; i++){
sum += nums[i];
}
return sum/count;
}
// To calculate median
float median(float* nums, int count){
float sorted[count];
copy(nums, nums+count, sorted);
sort(sorted, sorted + count);
if (count%2==0)
return (sorted[(count/2)-1] + sorted[count/2])/2;
else
return sorted[(count/2)];
}
// To calculate standard deviation
float std_dev(float* nums, int count, float mean){
float sum_of_squares_of_diffs = 0;
for(int i=0; i<count; i++){
sum_of_squares_of_diffs += pow(nums[i] - mean, 2);
}
return sqrt(sum_of_squares_of_diffs / (count-1));
}
int main(){
int n; //No. of inputs
cout << "Enter number of inputs: ";
cin >> n;
// Checks
if (n<1){
cout << "Input must be a non-zero positive number." << endl;
return 1;
}
if (n>100){
cout << "Input cannot be greater than 100." << endl;
return 1;
}
// Array to hold input data
float inputs[n];
// Opening and reading input file contents to the array
string line;
ifstream input_file ("input.txt");
if (input_file.is_open()){
int count=0;
while(getline(input_file, line) && count<n){
inputs[count] = stof(line);
count++;
}
if (count<n){
cout << "There are fewer numbers in the input file than the entered number." << endl;
return 1;
}
input_file.close();
}
else{
cout << "Unable to open input file." << endl;
return 1;
}
cout << "Inputs: ";
show(inputs, n);
float m = mean(inputs, n);
cout << "Mean: " << m << endl;
cout << "Standard Deviation: " << std_dev(inputs, n, m) << endl;
cout << "Median: " << median(inputs, n) << endl;
return 0;
}
Note on D111: Measured -- for new development, this will be zero
Note on D112: Counted. This is the number of lines you plan to delete from the base.
Note on D113: Counted. This is the number of lines you plan to modify from the base code.
Note on D114: T-B+D-R. This is calculated as the total product size adjusted for base code and reused code.
Note on D115: Counted. This is a count of the lines of source code that you included from a reuse library.
Note on D116: A+M. This is calculated as the number of added lines of code plus the number of lines of code modified from the base.
Note on C117: Estimate the number of lines of code of this assignment.
Note on D117: Measured. This is the total lines of code at the completion of the assignment.
Note on D118: Counted. This is a count of the lines of code in the assignment that have been placed into a reuse library.
Note on C130: Estimate how much time you plan to expend on this assignment.
Note on F283: BA + NO
Note on F284: Ensure actual LOC significantly correlates with estimated LOC. If not, use 0.
Note on F285: Ensure actual LOC significantly correlates with estimated LOC. If not, use 1.
Note on F286: B0 + B1*(P+M)
Note on F287: N+B-D-M+R
Note on F289: Not applicable if actual LOC is not significantly correlated with estimated LOC